## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
0 | 2/3 |  | 2023-10-23 | 2023-11-03 | Inactive
0 | 4/5 |  | 2023-11-06 | 2023-11-17 | Inactive
0 | 6/7 |  | 2023-11-20 | 2023-12-01 | Inactive
MST + Term Break
1 | 12/13 | Start development on the following: - SPmart Web Server (adapting from previous project) - LCD menus for SPmart self-checkout - Keypad programming for SPmart self-checkout | 2024-01-01 | 2024-01-12 | Closed
2 | 14/15 | Start development on the following: - Camera scanning functions - LCD menus and keypad for product scanning - Integration with SQL database for Product scanning Start integrating the following: - LCD Keypad for payment - RFID for payment Start Testing Containerisation: - Create Dockerfile, Docker-Compose & Build Images Finish development on the following: - SPmart Web Server - MySQL database | 2024-01-15 | 2024-01-26 | Closed
3 | 16/17 | Finish development on the following: - Product Scanning with Camera - Integration with SQL database (and Web Server) - Unit Tests with PyTest - System Tests Complete documents for submission: - Video demo - SRS doc - Sprint Planning - Test Report | 2024-01-29 | 2024-02-09 | Closed
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | Done | Sprint 1
2 | Web Server Development | As a Software Developer, I need to ensure the Web Server is functioning properly | Web Server CRUD works after modifying from previous project | 6 | 9 | Done | Sprint 1
3 | LCD Keypad Basic Functions | As a Hardware Developer, I need to ensure that the LCD and Keypad basic functions work | The basic LCD Keypad works, where Outputs are displayed & Inputs are registered | 2 | 2 | Done | Sprint 1
4 | SQL Database Development | As Software Developer, I need to define additional tables for the database to meet requirements | MySQL database modified to include new requirements | 2 | 1 | Done | Sprint 1
5 | Payment Functions | As a Hardware Developer, I need to ensure that LCD Keypad and RFID is integrated and functioning | Basic payment functions as expected | 5 | 5 | Done | Sprint 2
6 | Containerization | As a Software developer, I need to containerize all 3 images, and ensure that they can be deployed on the RPI | Docker containers built and ran succesfully in RPI | 5 | 18 | Done | Sprint 2
7 | Camera | As a Hardware Developer, i need to ensure that camera functions as expected | Camera can detect barcode in RPI | 1 | 3 | Done | Sprint 2
8 | Product Scanning functions | As a Hardware Developer, I have to ensure that camera can detect barcodes and fetch data from database | Fetch product from database using camera | 3 | 1 | Done | Sprint 3
9 | Database Integration | As a Software Developer, I need to ensure Web Server can modify products for self-checkout system in real time | Product attributes edited in real time is reflected in self checkout | 3 | 2 | Done | Sprint 3
10 | PyTest Integration | As Software Developer, I need to define Unit Tests | The PyTests shall be complete with all PyTests passing | 1 | 1 | Done | Sprint 3
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6